## Tasks
Task ID | Project | Participant | Category | Priority | Status | Start Date | Due Date | Completed Date | Estimated Hours | Actual Hours | Variance Hours | Completion % | On Time | Notes
101 | Sales Dashboard Refresh | PRKD | MySQL | High | Completed | 2026-09-01 | 2026-09-04 | 2026-09-04 | 6 | 6.5 | 0.5 | 100% | 1 | Prepare source data model - Initial model approved
102 | Sales Dashboard Refresh | PRKD | SQL | High | In Progress | 2026-09-08 | 2026-09-25 |  | 5 | 3 | -2 | 60% | 1 | Create KPI validation query - Add edge-case tests
103 | GitHub Workshop Materials | PRKD | Testing | Medium | Not Started | 2026-09-24 | 2026-09-30 |  | 3 |  | 0 | 0% | 1 | Review workshop repository - Check branches and permissions
104 | Data Quality Automation | PAAT | Documentation | Medium | Completed | 2026-09-02 | 2026-09-05 | 2026-09-05 | 4 | 3.5 | -0.5 | 100% | 1 | Define duplicate detection rules - Rules saved in project notes
105 | Data Quality Automation | PAAT | SQL | High | In Progress | 2026-09-07 | 2026-09-24 |  | 7 | 5.5 | -1.5 | 80% | 1 | Build duplicate records query - Waiting for one source column
106 | GitHub Workshop Materials | PAAT | Documentation | Low | Not Started | 2026-09-25 | 2026-10-02 |  | 2 |  | 0 | 0% | 1 | Add README examples - Use simple Markdown examples
107 | Monthly Reporting Workflow | ALZK | Excel | Medium | Completed | 2026-09-01 | 2026-09-03 | 2026-09-02 | 3 | 2.5 | -0.5 | 100% | 1 | Map monthly input files - File map shared with team
108 | Monthly Reporting Workflow | ALZK | Documentation | Medium | Completed | 2026-09-04 | 2026-09-08 | 2026-09-09 | 3 | 4 | 1 | 100% | 0 | Create import checklist - Completed one day late
109 | GitHub Workshop Materials | ALZK | Testing | High | In Progress | 2026-09-21 | 2026-09-24 |  | 4 | 2 | -2 | 50% | 1 | Test merge conflict scenario - Use shared SQL file
110 | Sales Dashboard Refresh | WERA | Power BI | Medium | Completed | 2026-09-03 | 2026-09-08 | 2026-09-08 | 6 | 6 | 0 | 100% | 1 | Design dashboard layout - Layout accepted
111 | Sales Dashboard Refresh | WERA | Power BI | Medium | Blocked | 2026-09-09 | 2026-09-22 |  | 5 | 2 | -3 | 40% | 0 | Configure drill-through page - Blocked by missing relationship
112 | GitHub Workshop Materials | WERA | Documentation | Low | Not Started | 2026-09-25 | 2026-10-01 |  | 3 |  | 0 | 0% | 1 | Update workshop screenshots - Capture GitHub Desktop screens
113 | Data Quality Automation | DADY | Testing | High | Completed | 2026-09-02 | 2026-09-09 | 2026-09-08 | 5 | 5 | 0 | 100% | 1 | Create data quality test cases - All expected outcomes documented
114 | Data Quality Automation | DADY | Python | High | In Progress | 2026-09-10 | 2026-09-26 |  | 8 | 4 | -4 | 55% | 1 | Automate exception summary - Prototype creates CSV output
115 | Monthly Reporting Workflow | DADY | Excel | Medium | Not Started | 2026-09-24 | 2026-09-29 |  | 4 |  | 0 | 0% | 1 | Validate report totals - Compare with prior month
116 | Monthly Reporting Workflow | MIWW | Excel | High | Completed | 2026-09-01 | 2026-09-07 | 2026-09-07 | 6 | 6.5 | 0.5 | 100% | 1 | Create monthly control sheet - Includes reconciliation section
117 | Monthly Reporting Workflow | MIWW | Excel | High | In Progress | 2026-09-08 | 2026-09-23 |  | 5 | 4 | -1 | 75% | 1 | Add formula error checks - Two checks remain
118 | GitHub Workshop Materials | MIWW | Git | Medium | Completed | 2026-09-18 | 2026-09-21 | 2026-09-20 | 2 | 1.5 | -0.5 | 100% | 1 | Create sample pull request - Pull request merged
119 | Sales Dashboard Refresh | KIPJ | SQL | Medium | Completed | 2026-09-04 | 2026-09-10 | 2026-09-10 | 4 | 4 | 0 | 100% | 1 | Prepare dashboard test data - Includes null and duplicate rows
120 | Sales Dashboard Refresh | KIPJ | Testing | High | In Progress | 2026-09-15 | 2026-09-28 |  | 6 | 2.5 | -3.5 | 35% | 1 | Run user acceptance test - First feedback collected
121 | Data Quality Automation | KIPJ | Documentation | Low | Not Started | 2026-09-28 | 2026-10-05 |  | 3 |  | 0 | 0% | 1 | Document exception handling - Add examples after testing
122 | Data Quality Automation | KRWO | SQL | Medium | Completed | 2026-09-01 | 2026-09-06 | 2026-09-06 | 5 | 4.5 | -0.5 | 100% | 1 | Profile source columns - Profile stored in workbook
123 | Monthly Reporting Workflow | KRWO | Documentation | Medium | In Progress | 2026-09-12 | 2026-09-25 |  | 4 | 2.5 | -1.5 | 65% | 1 | Prepare refresh instructions - Add troubleshooting section
124 | GitHub Workshop Materials | KRWO | Testing | High | Blocked | 2026-09-22 | 2026-09-23 |  | 3 | 1 | -2 | 25% | 1 | Verify final workshop files - Waiting for final participant list

## Summary
GitHub Desktop Workshop - Team Summary
Reference Date | 2026-09-23 |  | Change this date to refresh On Time results in Excel.
Participant | Total Tasks | Completed | In Progress | Blocked | Estimated Hours | Actual Hours | Variance Hours | Avg Completion | Completion Rate | On Time Tasks
PRKD | 3 | 1 | 1 | 0 | 14 | 9.5 | -4.5 | 53.33% | 33.33% | 3
PAAT | 3 | 1 | 1 | 0 | 13 | 9 | -4 | 60% | 33.33% | 3
ALZK | 3 | 2 | 1 | 0 | 10 | 8.5 | -1.5 | 83.33% | 66.67% | 2
WERA | 3 | 1 | 0 | 1 | 14 | 8 | -6 | 46.67% | 33.33% | 2
DADY | 3 | 1 | 1 | 0 | 17 | 9 | -8 | 51.67% | 33.33% | 3
MIWW | 3 | 2 | 1 | 0 | 13 | 12 | -1 | 91.67% | 66.67% | 3
KIPJ | 3 | 1 | 1 | 0 | 13 | 6.5 | -6.5 | 45% | 33.33% | 3
KRWO | 3 | 1 | 1 | 1 | 12 | 8 | -4 | 63.33% | 33.33% | 3
TOTAL / AVERAGE | 24 | 10 | 7 | 2 | 106 | 70.5 | -35.5 | 61.87% | 41.67% | 22

## Instructions
Shared Workshop File - Suggested Exercises
Step | Exercise | Action | Tool | Completed By | Notes
1 | Create a branch | Create a branch named feature/<your-initials>. | GitHub Desktop
2 | Edit a task | Change one status, completion value or note on the Tasks sheet. | Excel
3 | Add a row | Add one new task assigned to your initials. | Excel
4 | Commit changes | Use a short message that explains what changed. | GitHub Desktop
5 | Push branch | Publish or push the branch to the remote repository. | GitHub Desktop
6 | Create pull request | Describe the change and ask another participant for review. | GitHub
7 | Review SQL | Add a comment or a new SELECT query to the shared SQL file. | SQL editor
8 | Resolve a conflict | Two participants edit the same note and resolve the conflict together. | GitHub Desktop
Color legend
Blue text | Editable input
Black text | Formula or calculated value
Green text | Linked formula from another sheet
Gray text | Static label or instruction
Purple fill | Control value